## Project Planner
Yoga app
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Identify/Select Team & Team Structure | 1 | 5 | 1 | 4 | 0%
Establish Purpose | 1 | 6 | 1 | 6 | 0%
Determine Requirments | 2 | 4 | 2 | 5 | 0%
Create Flow Charts | 4 | 8 | 4 | 6 | 0%
Make Use Cases/ Activity Diagrams | 4 | 2 | 4 | 8 | 0%
Lay out architecture | 4 | 3 | 4 | 6 | 0%
Develope Prototype | 5 | 4 | 5 | 3 | 0%
Test Prototype | 5 | 2 | 5 | 5 | 0%
Analyze prototype runs | 5 | 2 | 5 | 6 | 0%
Make Improvements | 6 | 5 | 6 | 7 | 0%
Present Prototype to Company for Approval | 6 | 1 | 5 | 8 | 0%
Add any Additions Requested by Company | 9 | 3 | 9 | 3 | 0%
Create a Beta | 9 | 6 | 9 | 7 | 0%
Refine Beta | 9 | 3 | 9 | 1 | 0%
Present Beta to Company for Approval | 9 | 4 | 8 | 5 | 0%
Select Beta Testers | 10 | 5 | 10 | 3 | 0%
Run Beta to Testers | 11 | 2 | 11 | 5 | 0%
Analyze Beta Results | 12 | 6 | 12 | 7 | 0%
Make Improvements to Beta | 12 | 1 | 12 | 5 | 0%
Get Company Approval | 14 | 5 | 14 | 6 | 0%
Install and Deploy App | 14 | 8 | 14 | 2 | 0%
Analyze App as Users Use | 14 | 7 | 14 | 3 | 0%
Creat Any Needed Updates | 15 | 4 | 15 | 8 | 0%
Present and Receive Permission | 15 | 5 | 15 | 3 | 0%
Apply Updates | 15 | 8 | 15 | 5 | 0%
Maintain App | 16 | 28 | 16 | 30 | 0%